## Sheet1
Test Report - Tide System Testing
Test Cycle | Functional Testing - 1
Executed | Passed | 10
| Failed | 1
| Total | 11
Feature | No of Tests | %Tests Ececuted | %Tests Passed | Status | Observations
Home Promo | 1 | 100 | 100
P&G Redirect | 1 | 100 | 100
Live Chat | 1 | 100 | 100
Change Language | 1 | 100 | 100
Footer T&C | 1 | 100 | 100
P&G Display | 1 | 100 | 100
Navigation Wash | 1 | 100 | 100
Search Text | 1 | 100 | 100
Sign Up Valid | 1 | 100 | 100
Sign Up Invalid | 1 | 100 | 0 |  | Defect
Footer Powder | 1 | 100 | 100
Defects Priority | Logged | %Closed | %Invalid | %Open
P1
P2 | 1 | 0 | 0 | 100
P3 | 2 | 50 | 0 | 50
P4
P5
P6